## Container List
Container List
Container No. | Carrier | Container Step | Shipment ID | BOL No. | Seal No. | LOC | ETA Port Date | Chassis No. | Door/Yard No. | Actual Port Arrival Date | Port Appt. Date | Port Appt. Time | Port Pickup Date | Schedule In Date | DC Arrived Date | Offload Complete Date | Demurrage LFD | Detention Days (WD/CD) | Detention Expiry Date | DC Pull Date | Ctnr. Return Date | Shipping Line | Custom Hold | Ctnr. Size | Chassis Brand | Entrance Document ID | Terminal | Gate Code | Pickup Pass Code | Delivery Order No. | Updated By | Last Updated
TGBU8676553 | OA Express | Received | EE26030042 | 142600536567 | EMCCMY1995 | WOD | 2026-04-05 | TSXZ555278 | D11 | 2026-04-05 | 2026-04-08 12:00 | 46120.5 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 14(CD) | 2026-04-22 |  |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-10 14:12
EGSU1301833 | OA Express | DC Pull | EE26030042 | 142600536567 | EMCCPL7955 | WOD | 2026-04-05 | TSXZ461632 | B20 | 2026-04-05 | 2026-04-08 11:56 | 46120.4972 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-13 | 2026-04-09 | 14(CD) | 2026-04-22 | 2026-04-17 |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | susie.cassidy@oaexpress.com | 2026-04-17 07:53
TXGU5738994 | OA Express | Received | EE26030065 | 142600577239 | EMCWLV0754 | WOD | 2026-04-05 16:18 | HDMZ413867 | B24 | 2026-04-05 16:18 | 2026-04-10 08:25 | 46122.3507 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-15 | 2026-04-09 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | Direct Chassis Link |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-15 09:48
DRYU9829607 | OA Express | Received | EE26030065 | 142600577239 | EMCWLV0284 | WOD | 2026-04-05 16:18 | MCCZ411659 | B07 | 2026-04-05 16:18 | 2026-04-10 11:27 | 46122.4771 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-14 | 2026-04-09 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-14 14:10
EGSU1522773 | OA Express | Received | EE26030042 | 142600536567 | EMCCMX5935 | WOD | 2026-04-05 | MCCZ413458 | B23 | 2026-04-05 | 2026-04-10 13:34 | 46122.5653 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-13 | 2026-04-09 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-13 14:23
EGSU1636040 | OA Express | Received | EE26030042 | 142600536567 | EMCCNK4235 | WOD | 2026-04-05 | TSXZ465119 | B10 | 2026-04-05 | 2026-04-13 14:48 | 46125.6167 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-16 | 2026-04-09 | 14(CD) | 2026-04-27 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-16 14:10
EGSU6073232 | OA Express | Received | EE26030015 | 142600454595 | EMCWNM4954 | WOD | 2026-04-02 13:42 | DECZ401079 | A04 | 2026-04-02 13:42 | 2026-04-10 14:33 | 46122.6062 | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-08 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-15 09:49
EISU8574052 | OA Express | Received | EE26030065 | 142600577239 | EMCWLT1164 | WOD | 2026-04-05 16:18 | TSXZ485203 | B09 | 2026-04-05 16:18 | 2026-04-09 06:02 | 46121.2514 | 2026-04-09 | 2026-04-15 | 2026-04-14 | 2026-04-16 | 2026-04-09 | 14(CD) | 2026-04-23 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-16 14:11
TIIU4512571 | OA Express | Received | EE26030042 | 142600536567 | EMCCPL9795 | WOD | 2026-04-05 | TSXZ465304 | B01 | 2026-04-05 | 2026-04-13 16:11 | 46125.6743 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-09 | 14(CD) | 2026-04-27 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-16 14:11
EGSU6462846 | OA Express | Received | EE26030065 | 142600577239 | EMCWLT1104 | WOD | 2026-04-05 16:18 | DECZ401010 | B04 | 2026-04-05 16:18 | 2026-04-09 06:03 | 46121.2521 | 2026-04-09 | 2026-04-15 | 2026-04-14 | 2026-04-15 | 2026-04-09 | 14(CD) | 2026-04-23 |  |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-16 08:54
EGSU9314400 | OA Express | Received | EE26030042 | 142600536567 | EMCCNL7875 | WOD | 2026-04-05 | 1TSXZ555192 | B25 | 2026-04-05 | 2026-04-09 14:32 | 46121.6056 | 2026-04-09 | 2026-04-10 | 2026-04-14 | 2026-04-15 | 2026-04-09 | 14(CD) | 2026-04-23 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-15 09:48
CAIU4889515 | OA Express | Received | EE26030074 | MEDUWQ571301 | FX45655238 | WOD | 2026-04-11 | MCCZ411681 | B11 | 2026-04-11 | 2026-04-14 12:48 | 46126.5333 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-17 | 2026-04-16 | 10(WD) | 2026-04-27 |  |  | MSC | No | 40'HQ | OA Express Lease Chassis |  | B58 SSA OAK |  |  |  | pat.neigg@ship8.com | 2026-04-17 13:35
MSBU6596420 | OA Express | Received | EE26030074 | MEDUWQ571301 | FX45655219 | WOD | 2026-04-11 | MCCZ411642 | 117 | 2026-04-11 | 2026-04-15 09:58 | 46127.4153 | 2026-04-15 | 2026-04-16 | 2026-04-15 | 2026-04-17 | 2026-04-16 | 10(WD) | 2026-04-28 |  |  | MSC | No | 40'HQ | OA Express Lease Chassis |  | B58 SSA OAK |  |  |  | pat.neigg@ship8.com | 2026-04-17
MSBU7263552 | OA Express | Received | EE26030074 | MEDUWQ571301 | FX45655179 | WOD | 2026-04-11 | HDMZ407859 | B02 | 2026-04-11 | 2026-04-14 12:46 | 46126.5319 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-16 | 2026-04-16 | 10(WD) | 2026-04-27 |  |  | MSC | No | 40'HQ | Direct Chassis Link |  | B58 SSA OAK |  |  |  | veronica.ramirez@ship8.com | 2026-04-16 14:11
TGBU4482483 | OA Express | Received | EFP26020005 | 142600120549 | EMCRRJ2964 | WOD | 2026-04-02 13:42 | TSXZ485845 | C01 | 2026-04-02 13:42 | 2026-04-08 13:39 | 46120.5687 | 2026-04-09 | 2026-04-09 | 2026-04-08 | 2026-04-16 | 2026-04-08 | 14(CD) | 2026-04-23 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 09:16
EGSU9683115 | OA Express | DC Pull | EFP26020005 | 142600120549 | EMCRRF9304 | WOD | 2026-04-02 13:42 | DECZ400972 | A02 | 2026-04-02 13:42 | 2026-04-08 11:58 | 46120.4986 | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-14 | 2026-04-08 | 14(CD) | 2026-04-22 | 2026-04-17 |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | susie.cassidy@oaexpress.com | 2026-04-17 07:54
CAAU5780064 | OA Express | DC Pull | EFP26020007 | 142600351150 | EMCRRK4764 | WOD | 2026-04-02 13:42 | DECZ401183 | D21 | 2026-04-02 13:42 | 2026-04-08 11:26 | 46120.4764 | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-16 | 2026-04-08 | 14(CD) | 2026-04-22 | 2026-04-17 |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | susie.cassidy@oaexpress.com | 2026-04-17 07:53
TIIU5283130 | OA Express | DC Pull | EFP26010009 | 142504245158 | EMCRQV3564 | WOD | 2026-03-11 | TSXZ485424 | D23 | 2026-03-11 | 2026-04-07 09:59 | 46119.416 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-14 | 2026-03-29 | 14(CD) | 2026-04-21 | 2026-04-17 |  | Evergreen | No | 40'HQ | Trac Chassis | [5 empty] | susie.cassidy@oaexpress.com | 2026-04-17 07:52
CAAU5336255 | OA Express | DC Pull | EE26030013 | 142600454056 | EMCVLH3414 | WOD | 2026-04-02 13:42 | MCCZ411644 | D09 | 2026-04-02 13:42 | 2026-04-07 15:02 | 46119.6264 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-10 | 2026-04-08 | 14(CD) | 2026-04-21 | 2026-04-17 |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | susie.cassidy@oaexpress.com | 2026-04-17 07:51
EISU8323144 | OA Express | DC Pull | EFP26020005 | 142600120549 | EMCRRJ3944 | WOD | 2026-04-02 13:42 | EMCZ745204 | A06 | 2026-04-02 13:42 | 2026-04-08 11:58 | 46120.4986 | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-14 | 2026-04-08 | 14(CD) | 2026-04-22 | 2026-04-17 |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | susie.cassidy@oaexpress.com | 2026-04-17 07:49
TIIU5072688 | OA Express | Received | EFP26020007 | 142600351150 | EMCRRJ9284 | WOD | 2026-04-02 13:42 | DECZ401087 | D05 | 2026-04-02 13:42 | 2026-04-07 10:53 | 46119.4535 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-15 | 2026-04-08 | 14(CD) | 2026-04-22 |  |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-15 14:06
TLLU5902977 | OA Express | Received | EFP26020004 | 142600120531 | EMCRQW8674 | WOD | 2026-04-02 13:42 | OESZ806019 | A07 | 2026-04-02 13:42 | 2026-04-07 15:13 | 46119.634 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-14 | 2026-04-08 | 14(CD) | 2026-04-22 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-14 14:11
EITU9418572 | OA Express | Received | EFP26020007 | 142600351150 | EMCRRJ9894 | WOD | 2026-04-02 13:42 | GACZ402472 | B22 | 2026-04-02 13:42 | 2026-04-08 11:24 | 46120.475 | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-13 | 2026-04-08 | 14(CD) | 2026-04-22 |  |  | Evergreen | No | 40'HQ | Direct Chassis Link |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-13 14:23
EMCU8447332 | OA Express | Received | EFP26020004 | 142600120531 | EMCRRF6774 | WOD | 2026-04-02 13:42 | TSXZ485738 | C03 | 2026-04-02 13:42 | 2026-04-09 14:32 | 46121.6056 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-17 | 2026-04-08 | 14(CD) | 2026-04-23 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 13:32
DRYU9539763 | OA Express | DC Pull | EFP26020004 | 142600120531 | EMCRRF6814 | WOD | 2026-04-02 13:42 | MCCZ413452 | C08 | 2026-04-02 13:42 | 2026-04-08 13:03 | 46120.5437 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-15 | 2026-04-08 | 14(CD) | 2026-04-22 | 2026-04-17 |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | susie.cassidy@oaexpress.com | 2026-04-17 07:53
BEAU6316143 | OA Express | DC Pull | EE26030042 | 142600536567 | EMCCMY1075 | WOD | 2026-04-05 | DECZ400910 | D20 | 2026-04-05 | 2026-04-08 11:26 | 46120.4764 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 14(CD) | 2026-04-22 | 2026-04-17 |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | susie.cassidy@oaexpress.com | 2026-04-17 07:53
TGBU8027596 | OA Express | Received | EFP26020007 | 142600351150 | EMCRRJ9944 | WOD | 2026-04-02 13:42 | DECZ401385 | D28 | 2026-04-02 13:42 | 2026-04-09 14:33 | 46121.6062 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-16 | 2026-04-08 | 14(CD) | 2026-04-23 |  |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-16 14:12
EMCU8671152 | OA Express | Received | EFP26020005 | 142600120549 | EMCRRJ3954 | WOD | 2026-04-02 13:42 | DECZ401277 | C02 | 2026-04-02 13:42 | 2026-04-08 13:38 | 46120.5681 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-15 | 2026-04-08 | 14(CD) | 2026-04-22 |  |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-15 14:07
GAOU6314632 | OA Express | Received | EFP26020004 | 142600120531 | EMCRRF6644 | WOD | 2026-04-02 13:42 | DECZ401620 | A08 | 2026-04-02 13:42 | 2026-04-08 12:00 | 46120.5 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-15 | 2026-04-08 | 14(CD) | 2026-04-22 |  |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-15 14:06
TGBU8657208 | OA Express | Received | EFP26020007 | 142600351150 | EMCRRJ9364 | WOD | 2026-04-02 13:42 | AMPZ422928 | 108 | 2026-04-02 13:42 | 2026-04-08 11:10 | 46120.4653 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-15 | 2026-04-08 | 14(CD) | 2026-04-22 |  |  | Evergreen | No | 40'HQ | Direct Chassis Link |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-15
TRHU8364820 | OA Express | Received | EFP26020005 | 142600120549 | EMCRRJ2954 | WOD | 2026-04-02 13:42 | TSXZ407222 | C06 | 2026-04-02 13:42 | 2026-04-08 13:40 | 46120.5694 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-14 | 2026-04-08 | 14(CD) | 2026-04-22 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-14 14:13
EMCU8277679 | OA Express | Received | EFP26020007 | 142600351150 | EMCRRK4864 | WOD | 2026-04-02 13:42 | TSXZ421265 | C04 | 2026-04-02 13:42 | 2026-04-08 11:59 | 46120.4993 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-13 | 2026-04-08 | 14(CD) | 2026-04-22 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-14 09:18
TXGU7412137 | OA Express | Received | EE26030016 | 142600454617 | EMCWMW1884 | WOD | 2026-04-02 13:42 | MCCZ424053 | D14 | 2026-04-02 13:42 | 2026-04-09 14:33 | 46121.6062 | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | 2026-04-08 | 14(CD) | 2026-04-23 |  |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-10 14:14
CAAU5056296 | OA Express | Received | EFP26020010 | 142600216783 | EMCRRJ8154 | WOD | 2026-04-02 | DECZ401567 | D09 | 2026-04-02 13:42 | 2026-04-10 08:22 | 46122.3486 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-17 | 2026-04-08 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 14:12
EMCU8314601 | OA Express | Received | EFP26020010 | 142600216783 | EMCRRJ7834 | WOD | 2026-04-02 | MSCZ452699 | C12 | 2026-04-02 13:42 | 2026-04-10 13:41 | 46122.5701 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-17 | 2026-04-08 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | Direct Chassis Link |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 14:11
EMCU1521130 | OA Express | Received | EFP26020005 | 142600120549 | EMCRRF7974 | WOD | 2026-04-02 13:42 | TSXZ472295 | C11 | 2026-04-02 13:42 | 2026-04-09 12:29 | 46121.5201 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-17 | 2026-04-08 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 14:11
TCNU6570367 | OA Express | Received | EFP26020010 | 142600216783 | EMCRRJ8174 | WOD | 2026-04-02 | TSXZ485468 | A02 | 2026-04-02 13:42 | 2026-04-10 08:59 | 46122.3743 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-17 | 2026-04-08 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 13:33
EITU1193382 | OA Express | Received | EFP26020005 | 142600120549 | EMCRRF8904 | WOD | 2026-04-02 13:42 | MCCZ411679 | C08 | 2026-04-02 13:42 | 2026-04-09 11:15 | 46121.4688 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-17 | 2026-04-08 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 13:33
TXGU5955460 | OA Express | Received | EFP26020004 | 142600120531 | EMCRRF7774 | WOD | 2026-04-02 13:42 | AMPZ414602 | C07 | 2026-04-02 13:42 | 2026-04-10 05:50 | 46122.2431 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-17 | 2026-04-08 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | Direct Chassis Link |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 13:33
EGHU9384070 | OA Express | Received | EFP26020010 | 142600216783 | EMCRRJ8124 | WOD | 2026-04-02 | MCCZ411675 | A06 | 2026-04-02 13:42 | 2026-04-10 08:23 | 46122.3493 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-16 | 2026-04-08 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 09:17
EGSU1762394 | OA Express | Received | EFP26020010 | 142600216783 | EMCRRH8034 | WOD | 2026-04-02 | TSXZ461911 | A72 | 2026-04-02 13:42 | 2026-04-10 13:33 | 46122.5646 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-16 | 2026-04-08 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 09:15
EMCU9937756 | OA Express | Received | EFP26020005 | 142600120549 | EMCRRJ4544 | WOD | 2026-04-02 13:42 | MCCZ411595 | A73 | 2026-04-02 13:42 | 2026-04-09 12:39 | 46121.5271 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-16 | 2026-04-08 | 14(CD) | 2026-04-23 |  |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 09:14
EGSU6321010 | OA Express | DC Pull | EE26030042 | 142600536567 | EMCCNL7835 | WOD | 2026-04-05 | TSXZ436930 | B08 | 2026-04-05 | 2026-04-08 11:57 | 46120.4979 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-14 | 2026-04-09 | 14(CD) | 2026-04-22 | 2026-04-17 |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | susie.cassidy@oaexpress.com | 2026-04-17 07:54
EGHU9475150 | OA Express | Received | EFP26020004 | 142600120531 | EMCRRF7604 | WOD | 2026-04-02 13:42 | OESZ806043 | D29 | 2026-04-02 13:42 | 2026-04-09 11:14 | 46121.4681 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-16 | 2026-04-08 | 14(CD) | 2026-04-23 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-16 14:12
EMCU8589147 | OA Express | Received | EFP26020004 | 142600120531 | EMCRRF7834 | WOD | 2026-04-02 13:42 | TSXZ465672 | C09 | 2026-04-02 13:42 | 2026-04-08 11:59 | 46120.4993 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-15 | 2026-04-08 | 14(CD) | 2026-04-22 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-15
GAOU7311561 | OA Express | Received | EE26030062 | 142600536648 | EMCVLB4634 | WOD | 2026-04-05 17:00 | DECZ401293 | B06 | 2026-04-05 17:00 | 2026-04-10 13:31 | 46122.5632 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-15 | 2026-04-09 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | Evergreen |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-15
EGSU1613410 | OA Express | Received | EE26030042 | 142600536567 | EMCCMX6835 | WOD | 2026-04-05 | TSXZ485961 | B12 | 2026-04-05 | 2026-04-10 19:52 | 46122.8278 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-14 | 2026-04-09 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-14 14:14
GAOU6306909 | OA Express | Received | EE26030076 | 235600279550 | EMCXCV9894 | WOD | 2026-04-06 | MCCZ411594 | A74 | 2026-04-06 | 2026-04-10 13:33 | 46122.5646 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-14 | 2026-04-10 | 14(CD) | 2026-04-24 |  |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-14 14:14
TIIU4630492 | OA Express | Received | EFP26020005 | 142600120549 | EMCRRF9624 | WOD | 2026-04-02 13:42 | MCCZ411668 | A03 | 2026-04-02 13:42 | 2026-04-08 13:39 | 46120.5687 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-14 | 2026-04-08 | 14(CD) | 2026-04-22 |  |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-14 14:13
EGSU9203601 | OA Express | Received | EE26030042 | 142600536567 | EMCCNK2805 | WOD | 2026-04-05 | TSXZ555599 | A71 | 2026-04-05 | 2026-04-13 14:49 | 46125.6174 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-16 | 2026-04-09 | 14(CD) | 2026-04-27 |  |  | Evergreen | No | 40'HQ | Trac Chassis |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-16 14:13
EGSU9367077 | OA Express | Received | EFP26020009 | 142600216792 | EMCRRH8544 | WOD | 2026-04-02 13:42 | MCCZ413440 | C10 | 2026-04-02 13:42 | 2026-04-13 16:20 | 46125.6806 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-17 | 2026-04-08 | 14(CD) | 2026-04-27 |  |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | WBA5 BENT |  |  |  | pat.neigg@ship8.com | 2026-04-17 14:11
CAAU5350145 | OA Express | Received | EE26030016 | 142600454617 | EMCPSW6154 | WOD | 2026-04-02 13:42 | GACZ401641 | B03 | 2026-04-02 13:42 | 2026-04-09 14:31 | 46121.6049 | 2026-04-09 | 2026-04-10 | 2026-04-14 | 2026-04-15 | 2026-04-09 | 14(CD) | 2026-04-23 |  |  | Evergreen | No | 40'HQ | Direct Chassis Link |  | WBA5 BENT |  |  |  | veronica.ramirez@ship8.com | 2026-04-16 09:02
MSDU7114999 | OA Express | Received | EE26030085 | MEDUWQ571269 | FX45156667 | WOD | 2026-04-11 | MCCZ413451 | B21 | 2026-04-11 | 2026-04-14 12:47 | 46126.5326 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-17 | 2026-04-16 | 10(WD) | 2026-04-27 |  |  | MSC | No | 40'HQ | OA Express Lease Chassis |  | B58 SSA OAK |  |  |  | pat.neigg@ship8.com | 2026-04-17 13:35
TXGU5315478 | OA Express | Received | EE26030061 | 235600355281 | EMCXBC9664 | WOD | 2026-04-11 21:45 | MCCZ412067 | A75 | 2026-04-11 21:45 | 2026-04-15 09:56 | 46127.4139 | 2026-04-15 | 2026-04-16 | 2026-04-15 | 2026-04-17 | 2026-04-16 | 10(CD) | 2026-04-25 |  |  | Evergreen | No | 40'HQ | OA Express Lease Chassis |  | L738 GARDEN CITY TERMINAL |  |  |  | pat.neigg@ship8.com | 2026-04-17 09:29
MSNU6024735 | OA Express | Received | EE26030074 | MEDUWQ571301 | FX45139961 | WOD | 2026-04-11 | MCCZ411620 | B08 | 2026-04-11 | 2026-04-14 12:47 | 46126.5326 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-16 | 2026-04-16 | 10(WD) | 2026-04-27 |  |  | MSC | No | 40'HQ | OA Express Lease Chassis |  | B58 SSA OAK |  |  |  | pat.neigg@ship8.com | 2026-04-17 09:16