## EEC Requirement List
Enhancement No. | Department | Area | Project Name | Enhancement Title | Priority | Project Owner | Location | Hold | Status | Application Type | Reference Page | Related Story ID | Related Work ID | Estimated Finish Date | Aged Days | Requested Date | Requested By | Approve Date | Approve By | Completed Date | Last Updated Date | Last Updated By
EH26040027 | One Central PM team | China EEC(EEC,VSS, CCD,Express, etc.) | 关于一次性上导多个订单Cost&Dim.和Package type以及推单 | 关于一次性上导多个订单Cost&Dim.和Package type以及推单 | 2-Urgent | Cindy | SV3 | No | Development | Web Page | 相关页面 |  | 139376 | 2026-06-11 | 5 | 2026-04-22 20:30 | jinminna@jlachina.com | 2026-04-23 21:33 | fangfang@syncsoftinc.com |  | 2026-04-24 01:47 | fangfang@syncsoftinc.com
EH26040028 | logistics | China EEC(EEC,VSS, CCD,Express, etc.) | DG系统自动订舱 | DG系统自动订舱 | 2-Urgent | apple | SV2 | No | Development | Web Page | expeditors网站 |  | 139366 | 2026-04-30 | 6 | 2026-04-22 23:32 | wangyanni@jlachina.com | 2026-04-22 23:35 | yingyaping@jlachina.com |  | 2026-04-23 02:14 | sunligang@syncsoftinc.com
EH26040021 |  | China EEC(EEC,VSS, CCD,Express, etc.) |  | EEC更新需求--UCT--4.21 | 2-Urgent | liujiahong |  | No | Approved | Web Page | EEC |  |  |  | 6 | 2026-04-20 18:27 | liujiahong@jlachina.com | 2026-04-22 19:09 | yingyaping@jlachina.com |  | 2026-04-22 19:09 | yingyaping@jlachina.com
EH26040018 | Ecom | China EEC(EEC,VSS, CCD,Express, etc.) | Hardline Furniture/Art/Lighting division 不要工厂价回流 | Hardline Furniture/Art/Lighting division 不要工厂价回流 | 2-Urgent | Jessie Zhang |  | No | Development |  | Furniture initial order |  | 139265 | 2026-05-21 | 9 | 2026-04-16 02:51 | jessie.zhang@jlachina.com | 2026-04-19 05:44 | yingyaping@jlachina.com |  | 2026-04-19 18:58 | zhouyafei@syncsoftinc.cn
EH26030036 | Logistics | China EEC(EEC,VSS, CCD,Express, etc.) | Fabric 界面优化 | Fabric 界面自动生成Booking + 导出各家工厂码单 | 2-Urgent | Logistics | SV3 | No | Development | Web Page | 10 |  | 139042, 138993, 139096,139097 | 2026-05-21 | 29 | 2026-03-30 18:15 | yuyingdi@jlachina.com | 2026-03-30 20:18 | yingyaping@jlachina.com |  | 2026-04-14 00:15 | fangfang@syncsoftinc.com
EH25010014 | Production | China EEC(EEC,VSS, CCD,Express, etc.) | Auto Copy Item to 111 | Auto Copy Item to 111 | 1-Top Urgent | Heather Zhu | SV3 | Yes | Approved | Web Page | Item Master List |  |  |  | 474 | 2025-01-08 15:10 | heather.zhu@jlahome.com | 2025-01-09 13:50 | malijun@syncsoftinc.com |  | 2026-04-13 02:08 | zhouyafei@syncsoftinc.cn
EH25110001 | Production | China EEC(EEC,VSS, CCD,Express, etc.) | Item Master Data Update Auto Syndication | Item Master Data Update Auto Syndication | 3-General | Heather Zhu | FMT | No | Development | Web Page | Item Master List |  | 139002 | 2026-05-21 | 175 | 2025-11-04 10:33 | heather.zhu@jlahome.com | 2025-11-04 16:50 | yingyaping@jlachina.com |  | 2026-04-12 22:46 | zhouyafei@syncsoftinc.cn
EH26030037 |  | China EEC(EEC,VSS, CCD,Express, etc.) |  | 外销出运模块系统导出开票通知名称 | 2-Urgent | 吕亚楠 |  | No | Development | Web Page | 钉钉沟通 |  | 138915 | 2026-05-21 | 29 | 2026-03-30 18:16 | lvyanan@jlachina.com | 2026-03-30 20:24 | yingyaping@jlachina.com |  | 2026-04-07 01:06 | zhouyafei@syncsoftinc.cn
EH25110018 | UCT | China EEC(EEC,VSS, CCD,Express, etc.) | Purchased Order和Item Master List优化需求 | Purchased Order和Item Master List优化需求 | 2-Urgent | 刘婕 |  | No | Development |  | Purchased Order / Item Master List |  | 138879,138881 | 2026-05-21 | 152 | 2025-11-27 17:29 | liujie@jlachina.com | 2025-11-27 22:10 | yingyaping@jlachina.com |  | 2026-04-02 02:09 | zhouyafei@syncsoftinc.cn
EH26030033 | China logistics | China EEC(EEC,VSS, CCD,Express, etc.) | Eplus界面优化 | Eplus界面优化 | 2-Urgent | Angeline |  | No | Development | Web Page | Eplus |  | 138864 | 2026-05-21 | 34 | 2026-03-25 21:10 | yaojichun@jlachina.com | 2026-03-25 21:27 | yingyaping@jlachina.com |  | 2026-04-01 23:00 | zhouyafei@syncsoftinc.cn
EH26030030 |  | China EEC(EEC,VSS, CCD,Express, etc.) |  | 外销出运模块系统导出开票通知名称 |  | 吕亚楠 | SV2 | No | Additional Info | Web Page | 钉钉沟通 |  |  |  |  | 2026-03-23 23:09 | lvyanan@jlachina.com |  |  |  | 2026-03-24 22:44 | yexiaomiao@syncsoftinc.com
EH26030032 |  | China EEC(EEC,VSS, CCD,Express, etc.) | class code of new item in Furniture initial order | class code of new item in Furniture initial order |  | Jessie Zhang |  | No | Initial Review |  | Furniture initial order |  |  |  |  | 2026-03-24 20:21 | jessie.zhang@jlachina.com |  |  |  | 2026-03-24 20:21 | jessie.zhang@jlachina.com
EH26030013 |  | Back-End Data Recovery |  | New Product Categories for Bath |  | Jennie Jin |  | No | Initial Review | Web Page | Item Mater List |  |  |  |  | 2026-03-09 19:22 | jinzhenhong2@jlachina.com |  |  |  | 2026-03-09 19:22 | jinzhenhong2@jlachina.com
EH26030010 | Logistics | China EEC(EEC,VSS, CCD,Express, etc.) | Fabric 界面，在Shipment 界面直接导出ISF10+2 | Fabric 界面自动生成ISF表格 |  | Logistics |  | No | Initial Review | Web Page | 10 |  |  |  |  | 2026-03-09 02:07 | yuyingdi@jlachina.com |  |  |  | 2026-03-09 02:20 | yuyingdi@jlachina.com
EH26020029 | 供应链业务管理部 | Ecom General(Ecom, Eplus, VIN, etc.) | VIN PRODUCT DESIGN 模块搭建申请 | VIN PRODUCT DESIGN 模块搭建申请 | 2-Urgent | wangjingying |  | No | Approved | Web Page | VIN-多个页面 |  |  |  | 62 | 2026-02-25 22:59 | wangjingying@jlachina.com | 2026-02-25 23:05 | yingyaping@jlachina.com |  | 2026-02-25 23:05 | yingyaping@jlachina.com
EH26020003 | 后台支持5组 | China EEC(EEC,VSS, CCD,Express, etc.) | 系统优化 | QC 和VSS页面增加新功能 | 3-General | chenjun |  | No | Approved | Web Page | EEC QC Iinspection |  |  |  | 83 | 2026-02-04 22:03 | chenjun@jlachina.com | 2026-02-04 22:15 | yingyaping@jlachina.com |  | 2026-02-04 22:15 | yingyaping@jlachina.com
EH25110006 |  | Back-End Data Recovery |  | 帮忙还原成未签收状态 |  | 商务中心 |  | No | Initial Review | Web Page | Express |  |  |  |  | 2025-11-10 18:36 | bc-cn@jlachina.com |  |  |  | 2025-11-10 18:36 | bc-cn@jlachina.com
EH25090020 |  | China EEC(EEC,VSS, CCD,Express, etc.) | running change item切换 | running change item number切换 |  | Grace Chen |  | No | Initial Review | Web Page | Ecom retail data |  |  |  |  | 2025-09-19 10:39 | grace.chen@jlahome.com |  |  |  | 2025-09-19 10:39 | grace.chen@jlahome.com
EH25050027 | UCT | Back-End Data Recovery |  | Update Item Pattern and Color |  | Lisa Gao |  | No | Initial Review | Web Page | Item Master List |  |  |  |  | 2025-05-27 19:35 | gaoli@jlachina.com |  |  |  | 2025-05-27 19:35 | gaoli@jlachina.com
EH25050003 | China logistics | China EEC(EEC,VSS, CCD,Express, etc.) |  | Shipping Line界面更新需求 |  | Angeline |  | No | Additional Info | Web Page | Shipping Line |  |  |  |  | 2025-05-05 22:44 | yaojichun@jlachina.com |  |  |  | 2025-05-09 01:43 | yingyaping@jlachina.com
EH25020033 |  | China EEC(EEC,VSS, CCD,Express, etc.) |  | EEC 更新需求 | 3-General | liujiahong | WOD | Yes | Approved | Web Page | EEC |  |  |  | 432 | 2025-02-20 00:24 | liujiahong@jlachina.com | 2025-02-20 00:52 | yingyaping@jlachina.com |  | 2025-04-29 00:50 | zhuwenting@syncsoftinc.cn
EH25040006 |  | Back-End Data Recovery |  | Basic DI更新 Cost 4.8 |  | liujiahong |  | No | Initial Review | Web Page | EEC |  |  |  |  | 2025-04-07 20:04 | liujiahong@jlachina.com |  |  |  | 2025-04-07 20:04 | liujiahong@jlachina.com
EH25030025 |  | China EEC(EEC,VSS, CCD,Express, etc.) |  | EEC 系统：QC 优化更新需求 |  | liujiahong |  | No | Additional Info | Web Page | EEC |  |  |  |  | 2025-03-12 19:29 | liujiahong@jlachina.com |  |  |  | 2025-03-13 21:47 | yingyaping@jlachina.com
EH25020030 | QC | China EEC(EEC,VSS, CCD,Express, etc.) | QC Inspection modular | QC Inspection modular |  | Jane Jin |  | No | Initial Review | Web Page | NEW |  |  |  |  | 2025-02-19 11:17 | grace.chen@jlahome.com |  |  |  | 2025-02-19 11:17 | grace.chen@jlahome.com
EH25010004 | Logistics Team | China EEC(EEC,VSS, CCD,Express, etc.) | Booking sys | 123 |  | Logistics Team |  | No | Initial Review | Web Page | 10 |  |  |  |  | 2025-01-05 23:25 | yuyingdi@jlachina.com |  |  |  | 2025-01-05 23:25 | yuyingdi@jlachina.com
EH24120025 |  | China EEC(EEC,VSS, CCD,Express, etc.) |  | EEC 更新需求 |  | liujiahong |  | No | Additional Info | Web Page | EEC |  |  |  |  | 2024-12-18 18:28 | liujiahong@jlachina.com |  |  |  | 2024-12-18 20:43 | yingyaping@jlachina.com
EH24110034 | logistics | China EEC(EEC,VSS, CCD,Express, etc.) |  | Contract 页面更新 | 3-General | Logistics | WOD | No | Initial Review | Web Page | Contract |  |  |  |  | 2024-11-28 18:00 | suxu@jlachina.com | 2024-12-02 09:12 | heather.zhu@jlahome.com |  | 2024-12-05 00:32 | suxu@jlachina.com
EH24020034 | 财务部 | China EEC(EEC,VSS, CCD,Express, etc.) |  | EEC业务评估报表开发 |  | 沈欢欢 |  | No | Initial Review |  | Payment application |  |  |  |  | 2024-02-29 20:53 | shenhuanhuan@scmhome.com |  |  |  | 2024-02-29 20:59 | shenhuanhuan@scmhome.com
EH24010046 | Ecom team 5 | Back-End Data Recovery | Negative Review Fiing | Request to delete/close cases |  | Gaz |  | No | Initial Review | Web Page | Review management |  |  |  |  | 2024-01-30 22:00 | zhengshaofeng@scmhome.com |  |  |  | 2024-01-30 22:00 | zhengshaofeng@scmhome.com