## EEC Requirement List
Enhancement No. | Department | Area | Project Name | Enhancement Title | Priority | Analyst | Project Owner | Location | Hold | Status | Application Type | Reference Page | Related Story ID | Related Work ID | Estimated Finish Date | Aged Days | Requested Date | Requested By | Approve Date | Approve By | Completed Date | Last Updated Date | Last Updated By
EH26060007 | Accounting | US Accounting | DI/POE orders 自动创建shipment | DI/POE orders 自动创建shipment | 1-Top Urgent | fangfang@syncsoftinc.com | Daisy Liu | SV3 | No | Development | Web Page | Distribution Mgt |  | 140699，140681 | 2026-07-30 | 29 | 2026-06-03 09:20 | liudan@syncsoftinc.cn | 2026-06-03 09:21 | liudan@syncsoftinc.cn |  | 2026-07-01 02:05 | fangfang@syncsoftinc.com
EH26050001 | Accounting | US Accounting | MACOLA 200 customer 添加retail order no. 字段 | MACOLA 200 customer 添加retail order no. 字段 | 2-Urgent | hulinjuan@syncsoftinc.com | Daisy Liu | WOD | No | Development | Web Page | MACOLA 200 |  | 140711 | 2026-07-09 | 58 | 2026-05-05 18:34 | liudan@syncsoftinc.cn | 2026-05-05 18:40 | liudan@syncsoftinc.cn |  | 2026-06-30 02:04 | hulinjuan@syncsoftinc.com
EH26060014 | SALES/AR | US Accounting | AR AMAZON ALLOWANCE IMPORT | AR AMAZON ALLOWANCE IMPORT CHANGE | 1-Top Urgent | hulinjuan@syncsoftinc.com | Nichol Zhang | WOD | No | Development | Web Page | EEC |  | 140268,140288 | 2026-07-09 | 24 | 2026-06-08 15:26 | janis.auyang@jlahome.com | 2026-06-08 15:26 | janis.auyang@jlahome.com |  | 2026-06-28 23:04 | hulinjuan@syncsoftinc.com
EH26060031 | AR | US Accounting | Chargeback Accounting Process Page Update | Chargeback Accounting Process Page Update | 1-Top Urgent | fangfang@syncsoftinc.com | JANIS AUYANG | SV3 | No | Development | Web Page | EEC |  | 140676 | 2026-07-30 | 14 | 2026-06-18 11:11 | janis.auyang@jlahome.com | 2026-06-18 11:15 | janis.auyang@jlahome.com |  | 2026-06-28 22:53 | fangfang@syncsoftinc.com
EH26060033 | AR | US Accounting | EDI 812 report 批量导出 | EDI 812 report 批量导出 | 2-Urgent |  | Daisy Liu |  | No | Approved | Web Page | EDI |  |  |  | 10 | 2026-06-22 01:50 | liudan@syncsoftinc.cn | 2026-06-22 01:53 | liudan@syncsoftinc.cn |  | 2026-06-22 01:53 | liudan@syncsoftinc.cn
EH26020024 | Accounting | US Accounting | Net Sales Report | Net Sales Report | 2-Urgent | fangfang@syncsoftinc.com | Lucas Yuan | SV3 | No | Development | Web Page | Crytal report: Co001Co111 Net sales-cost report by Cust CU |  | 140321 | 2026-07-30 | 128 | 2026-02-24 21:53 | lucas.yuan@jlahome.com | 2026-02-24 21:54 | lucas.yuan@jlahome.com |  | 2026-06-22 00:25 | fangfang@syncsoftinc.com
EH26020022 | Accounting | US Accounting | Modified Sales / Cost Report | Modified Sales / Cost Report | 1-Top Urgent | fangfang@syncsoftinc.com | Lucas | SV3 | No | Development | Web Page | Crytal report: Co001Co111 Modified Sales and Cost Report Re-writeALT2 |  | 140516 | 2026-07-09 | 129 | 2026-02-23 22:17 | lucas.yuan@jlahome.com | 2026-02-23 22:19 | lucas.yuan@jlahome.com |  | 2026-06-22 00:24 | fangfang@syncsoftinc.com
EH26060018 | ACCTG | US Accounting | AP LOG MANUAL (EXCEL) FILE | AP LOG MANUAL (EXCEL) FILE | 3-General | yexiaomiao@syncsoftinc.com | TREY NGUYEN | SV2 | No | Development | Web Page | PAYMENT OUTLOOK |  | 140325 | 2026-07-09 | 17 | 2026-06-10 14:02 | trey.nguyen@jlahome.com | 2026-06-15 16:22 | yexiaomiao@syncsoftinc.com |  | 2026-06-15 16:22 | yexiaomiao@syncsoftinc.com
EH25050015 | AR | US Accounting | Tiktok Temu Statement Report Analysis | Tiktok Temu Statement Report Analysis | 2-Urgent |  | Janis Auyang, Daisy Liu |  | No | Approved | Web Page | EEC |  |  |  | 29 | 2025-05-20 02:01 | janis.auyang@jlahome.com | 2026-06-03 10:42 | liudan@syncsoftinc.cn |  | 2026-06-03 10:42 | liudan@syncsoftinc.cn
EH26050019 | Accounting | US Accounting | PO Transfer Mgt 页面添加数据 -1 | PO Transfer Mgt 页面添加数据 -1 | 1-Top Urgent | fangfang@syncsoftinc.com | Daisy Liu | SV3 | No | Development | Web Page | PO Transfer Mgt |  | 140005 | 2026-07-02 | 36 | 2026-05-27 18:52 | liudan@syncsoftinc.cn | 2026-05-27 18:55 | liudan@syncsoftinc.cn |  | 2026-05-27 23:49 | fangfang@syncsoftinc.com
EH26020025 | Accounting | US Accounting | AR CM/DM Reports | AR CM/DM | 2-Urgent |  | Lucas Yuan |  | No | Approved | Web Page | Crytal report: CR_DR Monthly List_001 |  |  |  | 128 | 2026-02-24 22:10 | lucas.yuan@jlahome.com | 2026-02-24 22:10 | lucas.yuan@jlahome.com |  | 2026-02-24 22:10 | lucas.yuan@jlahome.com
EH26020002 | Accounting | US Accounting | allocate COSTCO RTV items | allocate COSTCO RTV items | 1-Top Urgent |  | Daisy Liu |  | No | Approved | Web Page | costco return data |  |  |  | 150 | 2026-02-02 22:56 | liudan@syncsoftinc.cn | 2026-02-02 23:00 | liudan@syncsoftinc.cn |  | 2026-02-02 23:00 | liudan@syncsoftinc.cn
EH25070029 | Accounting | US Accounting | Olliix Commission | Olliix Commission | 3-General |  | Daisy / Lucas |  | No | Approved | Web Page | Commission Report |  |  |  | 329 | 2025-07-21 19:07 | lucas.yuan@jlahome.com | 2025-08-07 00:56 | liudan@syncsoftinc.cn |  | 2025-08-07 00:56 | liudan@syncsoftinc.cn